## Instructions
Department of Governmet Services
Contract risk segmentation tool
Context
The contract risk segmentation tool has been developed to identify the overall procurement risks associated with a category of goods and services and to identify individual risks at the procurement activity level for each contract. The outcome of an analysis can allocate a procurement to a particular contract management segment. The contract risk segmentation tool allows the following factors to be documented: • all risks to be identified • the likelihood and impact to be determined. • risk treatment strategies to be detailed, and • the benefit of these strategies to be assessed. The tool is used to determine a risk score based on likelihood, impact and treatment strategies for the risks identified. The tool also allows for the assessment of different treatment strategies against the identified risks mitigate the severity of the risks. This helps to determine the level or scalability of contract management that the category or the contract for a procurement activity requires throughout its life.
Instructions
1 | Open the 'risk assessment tool" tab and fill in the information required within section 1
2 | Next, move to section 3 and start completing the risk assessment, starting with the 'initial risk identified' area
2a | In the 'initial risk identified' area, fill in the risk under the 'risk identified' box
2b | Determine how likely the risk is to happen – click on the cell under 'likelihood' which corresponds to the risk being looked at and select one of the four options, Low, Moderate, High or Very High
2c | Determine the impact if the risk does happen – click on the cell under 'Impact' which corresponds to the risk being looked at and select one of the four options, Low, Moderate, High or Very High
3 | This provides a risk score. The risk score is created by multiplying two numbers together to give a score out of 10. The score associated with the 'likelihood' and 'impact' can be changed in the tables below these instructions
4 | Follow the same process for 'risk following treatment' used to complete the risks in the 'initial risk identified' area
5 | Once all the risks and the treatment strategies have been identified, section 2 provides the overall risk score. This is made up of the maximum score achieved in any one risk.
6 | Once the overall risk assessment has been completed you can use this to help decide contract segmentation.
Risk scores
| Likelihood | Score
| Low | 0.3
| Moderate | 0.5
| High | 0.7
| Very high | 1
| Impact | Score
| Low | 4
| Moderate | 6
| High | 8
| Very high | 10
If any risk scores are changed note below the reason why they have changed:
The KPIs, performance target, measurement and purpose can all be changed as the Agency requires. to change them, delete the data in the cells and enter in the new information
There are grey boxes under 'risk identified' which allow the user to key in data, key in one risk per line
The "Variance from Acceptable Score" will automatically calculate based on the current month score and the target the supplier was set
Copy the variance value from the "Supplier Scorecard" sheet
The KPIs, performance target, measurement and purpose can all be changed as the Agency requires. to change them, delete the data in the cells and enter in the new information
When the cell is selected a drop-down arrow appears  select the relevant likelihood
Calculated risk score
When the cell is selected a drop-down arrow appears  select the relevant likelihood
Risk score and indication if the risk is low risk (5 or below) or high risk (above 5)
Risk score following treatment

## Risk assessment tool
Contract risk segmentation tool
NOTE: THIS IS AN INTERACTIVE TOOL FOR USE
[insert here location where contract segmentation analysis tool is saved]
Section 1 | Contract name: |  |  |  | Review date:
| Supplier: |  |  |  | Next review due:
| Contract number: |  |  |  | Contract value/expenditure: | CV = $ E = $
Scope of the contract:
Section 2 | Overall risk score: | Initial risk score |  | 0 | Risk score following treatment |  |  | 0
Section 3 | Initial risk identified |  |  |  | Risk following treatment
| Risk identified | Likelihood | Impact | Risk score | Treatment strategy | Likelihood | Impact | Risk score